## Instructions
How to Use This Gantt Chart Template | For detailed instructions, visit our full guide:
https://www.teamgantt.com/free-gantt-chart-excel-template
📝 Task Table (enter your project details here)
Add each task, phase, or milestone in the Task Table tab.
Fill in Start Date, End Date, % Complete, Assigned To, and Priority.
Columns with formulas update automatically:
✅ Duration = End Date - Start Date + 1
✅ Completed = Duration * % Complete
✅ Remaining = Duration - Completed
Use WBS numbers (1, 1.1, 1.2, etc.) to organize phases and subtasks.
Leave group rows at 0% Complete so they show as dividers without skewing progress.
📊 Gantt Chart (visual project timeline)
The Gantt Chart tab updates automatically as you edit the Task Table.
Task bars display start and end dates; progress shows inside the bars.
Keep phase bars neutral (e.g., gray) and milestones gold for clarity.
📈 Dashboard (project snapshot)
The Dashboard tab shows:
✅ Total project duration
✅ Overall % completion
✅ Days remaining
✅ Task breakdown (not started, in progress, complete)
Metrics update automatically based on the Task Table.
“Not started” excludes group rows for accuracy.
💡 Tips
Use Predecessors to note dependencies (by WBS number).
If the Gantt chart doesn’t print fully:
1. Go to Page Layout → Print Area → Clear Print Area.
2. Reset the print area to include your full chart.

## Dashboard
Project: Consultant AI
Project owner: [Your Name]
Total project duration | Overall completion | Days remaining
89 | 20.56% | 65
Tasks complete | Tasks in progress | Tasks not started
3 | 2 | 14
Note on A4: Formula: =MAX(EndDateColumn) - MIN(StartDateColumn) + 1 (total calendar days across the project)
Note on B4: Formula: =AVERAGE(SelectedTaskPercentCompleteCells) (average % complete across task rows only; group rows are excluded)
Note on C4: Formula: =MAX(0, MAX(EndDateColumn) - TODAY()) (calendar days left until project end; shows 0 if overdue)
Note on A7: Formula: =COUNTIF(PercentCompleteColumn,1) (counts tasks at 100% complete)
Note on B7: Formula: =COUNTIFS(PercentCompleteColumn,">0",PercentCompleteColumn,"<1") (counts tasks with partial progress)
Note on C7: Formula: =SUMPRODUCT(((%CompleteRange=0)+(%CompleteRange="")>0)*(ISNUMBER(SEARCH(".",WBSRange&"")))) (counts tasks at 0% complete or blank; excludes group rows by only counting WBS numbers with decimals)

## Task Table
WBS # | Task Name | Start Date | End Date | Duration | % Complete | Completed | Remaining | Assigned To | Priority | Predecessor
1 | Initiation & Requirements | 2026-09-21 | 2026-10-16 | 26 | 85.16% | 22.1419 | 3.8581
1.1 | Review existing Consultant AI prototype and codebase | 2026-09-21 | 2026-09-25 | 5 | 100% | 5 | 0 | Student | High
1.2 | Requirements interviews with ISO 9001 consultant; user stories | 2026-09-28 | 2026-10-09 | 12 | 100% | 12 | 0 | Student + Consultant | High | 1.1
1.3 | Milestone: Project idea submitted | 2026-10-02 | 2026-10-02 | 1 | 100% | 1 | 0 | Student | High | 1.1
1.4 | Project proposal and Gantt chart | 2026-10-05 | 2026-10-16 | 12 | 70% | 8.4 | 3.6 | Student + Supervisor | High | 1.2
1.5 | Milestone: Proposal submitted | 2026-10-16 | 2026-10-16 | 1 | 0% | 0 | 1 | Student | High | 1.4
2 | Platform Hardening & Testing | 2026-10-19 | 2026-11-06 | 19 | 0% | 0 | 19
2.1 | Automated test suite (pytest) and GitHub Actions CI | 2026-10-19 | 2026-10-30 | 12 | 0% | 0 | 12 | Student | High | 1.5
2.2 | Retrieval evaluation question set and improvements | 2026-10-19 | 2026-11-06 | 19 | 0% | 0 | 19 | Student + Consultant | High | 1.2
2.3 | Deployment hardening (Docker, nginx, backups) | 2026-11-02 | 2026-11-06 | 5 | 0% | 0 | 5 | Student | Medium | 2.1
3 | Golden Templates | 2026-11-02 | 2026-11-20 | 19 | 0% | 0 | 19
3.1 | Design placeholder schema for ISO 9001 documents | 2026-11-02 | 2026-11-06 | 5 | 0% | 0 | 5 | Student + Consultant | High | 1.2
3.2 | Generate Word/Excel golden templates from client projects | 2026-11-09 | 2026-11-20 | 12 | 0% | 0 | 12 | Student | High | 3.1
3.3 | Milestone: Golden templates demo | 2026-11-20 | 2026-11-20 | 1 | 0% | 0 | 1 | Student + Consultant | High | 3.2
4 | Template Fill-in | 2026-11-23 | 2026-12-04 | 12 | 0% | 0 | 12
4.1 | Company-details intake form and data model | 2026-11-23 | 2026-11-27 | 5 | 0% | 0 | 5 | Student | High | 3.3
4.2 | Generate complete client document package | 2026-11-25 | 2026-12-04 | 10 | 0% | 0 | 10 | Student | High | 4.1
4.3 | Milestone: Feature complete | 2026-12-04 | 2026-12-04 | 1 | 0% | 0 | 1 | Student | High | 4.2
5 | Evaluation & Delivery | 2026-12-07 | 2026-12-18 | 12 | 0% | 0 | 12
5.1 | User acceptance testing with consultant | 2026-12-07 | 2026-12-11 | 5 | 0% | 0 | 5 | Student + Consultant | High | 4.3
5.2 | Final report and documentation | 2026-12-07 | 2026-12-16 | 10 | 0% | 0 | 10 | Student | High | 5.1
5.3 | Final presentation and demo | 2026-12-17 | 2026-12-17 | 1 | 0% | 0 | 1 | Student + Supervisor | High | 5.2
5.4 | Milestone: Final submission | 2026-12-18 | 2026-12-18 | 1 | 0% | 0 | 1 | Student | High | 5.3
Note on E1: Formula: =End Date - Start Date + 1 (counts both start and end dates)
Note on F1: Note: For group rows, either leave at 0% (simpler, for structure only) or use a weighted average formula to calculate progress across all tasks in the group. Weighted average formula: =SUMPRODUCT(DurationRange, PercentCompleteRange) / SUM(DurationRange)
Note on G1: Formula: =Duration * %Complete (portion of task finished)
Note on H1: Formula: =Duration - Completed (days still left to finish)